## Sheet1
[SwiftScout]
Product Backlog
Unique ID | Task | Sprint | Estimated Time (Minutes) | Time After Iteration 1 | Time After Iteration 2
1 | Plan and Design |  | 680 | 480 | 0
1.01 | Create Initial UML Activity Diagram | 1 | 45 | 35 |  | Use index colors to show revisions on task time
1.02 | Create Initial UML Class Diagram | 1 | 45 | 30
1.03 | Create Initial Dependency Diagram | 1 | 45 | 25 |  | Index | Information
1.04 | Create Backlogs | 1 | 60 | 40 |  |  | Target Time
1.05 | Download and Install Dependencies | 1 | 30 | 20 |  |  | Revised Target Time
1.06 | Set Up File Structure | 1 | 45 | 30 |  |  | Actual Time Taken
1.07 | Write Basic Stubs for Nodes | 1 | 60 | 40 |  |  | New Task Added
1.08 | Define Level 1 Unit Tests | 1 | 60 | 50 |  |  | Deleted Task
1.09 | Set Up Launch Files | 1 | 45 | 30
1.10 | Set Up Object Detection Using Camera | 1 | 50 | 40
1.11 | Create Initial ROS2 Nodes | 1 | 60 | 50
1.12 | Write Tests for Stubs and Nodes | 1 | 60 | 40
1.13 | Configure CI/CD for GitHub Actions | 1 | 45 | 35
2 | Implementation |  | 880 |  | 680
2.01 | Implement Goal Publisher Node | 2 | 60 |  | 45
2.02 | Implement Search Logic Node | 2 | 60 |  | 50
2.03 | Create ROS2 Camera Subscriber | 2 | 60 |  | 40
2.04 | Link Nodes in Launch Files | 2 | 60 |  | 30
2.05 | Test Multi-Robot Navigation | 2 | 90 |  | 60
2.06 | Write Unit Tests for Nodes | 2 | 120 |  | 90
2.07 | Debug and Optimize Node Connections | 2 | 120 |  | 100
2.08 | Test Object Detection Integration | 2 | 90 |  | 70
2.09 | Implement Error Handling in Nodes | 2 | 60 |  | 40
2.10 | Verify Object Detection Using Camera | 2 | 90 |  | 70
2.11 | Enhance Launch File with Parameters | 2 | 60 |  | 40
| Remaining effort |  |  | 680 | 880
| Extra effort time |  |  | -200 | -200
| Total effort time per Iteration |  | 1560 | 480 | 680
| Total effort time |  | 1560 | 480 | 680